## Weekly Gantt Chart (W1-W40)
|  | QUARTER 1 (Weeks 1 – 13) | [12 empty] | QUARTER 2 (Weeks 14 – 26) | [12 empty] | QUARTER 3 (Weeks 27 – 35) | [8 empty] | (Weeks 36 – 40)
|  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct
Task Code | Task Name | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40
1.0 | Research & Planning
1.0.1 | Research and Requirement Analysis
1.0.2 | Client Meeting / Approval | bar: Jan W3 to Feb W5
1.0.3 | UI/UX Design & Prototyping
1.1 | Account Management
1.1.1 | Sign Up
1.1.2 | Sign In | bar: Mar W9 to Mar W10
1.1.3 | Recover Account
1.1.4 | Sign Out | bar: Mar W11
1.1.5 | Profile Management
1.2 | Core Platform Setup
1.2.1 | Application Layout and Navigation
1.2.2 | Design System and Styling | bar: Mar W11 to Mar W12
1.2.3 | State and Data Utilities
1.2.4 | Authentication Guards and Middleware | bar: Mar W12 to Mar W13
1.3 | Tenant Discovery Portal
1.3.1 | Map-Based Search | bar: Apr W14 to Apr W15
1.3.2 | Location Suggestions
1.3.3 | Listing Filters and Cards | bar: Apr W16 to Apr W17
1.3.4 | Property Details
1.3.5 | Saved Listings | bar: May W18
1.4 | Applications and Lease Management
1.4.1 | Application Submission | bar: May W18 to May W19
1.4.2 | Application Timeline
1.4.3 | Application Review Workflow | bar: May W20 to May W21
1.4.4 | Lease Generation
1.4.5 | Digital Lease Signing | bar: Jun W22 to Jun W23
1.4.6 | Renewal and Move-Out Tracking
1.5 | Property and Unit Management
1.5.1 | Property Registration
1.5.2 | Property Verification Support | bar: Jun W23 to Jun W24
1.5.3 | Modular Floor Planner
1.5.4 | Grid Snapping and Layout Tools | bar: Jun W25 to Jun W26
1.5.5 | Unit Listing Wizard
1.5.6 | Unit Media Management | bar: Jun W26
1.5.7 | Listing Status Management
1.6 | Financial Operations
1.6.1 | Ledger and Invoice Tracking
1.6.2 | Invoice Breakdown Engine | bar: Jul W28 to Jul W29
1.6.3 | Receipt Upload and Verification
1.6.4 | Payment History Views | bar: Jul W30
1.6.5 | Report Exporting
1.6.6 | Export History and Audit Logs | bar: Aug W31
1.6.7 | Date Range Filters
1.7 | Maintenance, Messaging, and AI
1.7.1 | Maintenance Request Tracking
1.7.2 | Maintenance Status Updates | bar: Aug W32
1.7.3 | Real-Time Messaging
1.7.4 | Presence and Read Indicators | bar: Aug W33
1.7.5 | Media and File Sharing
1.7.6 | AI Assistant and RAG Context | bar: Aug W33 to Aug W34
1.7.7 | Landlord Analytics
1.7.8 | Message Moderation | bar: Aug W35
1.8 | Admin Governance
1.8.1 | System Monitoring Dashboard | bar: Aug W34 to Aug W35
1.8.2 | Registration Review Dashboard
1.8.3 | Internal Administrative Notes | bar: Aug W35
1.8.4 | User Management Tools
1.8.5 | Secure Sign-Out | bar: Sep W36
1.9 | Testing and Deployment
1.9.1 | Unit and Integration Testing | bar: Sep W36
1.9.2 | Security and Access Review
1.9.3 | Bug Fixing and Refinement | bar: Sep W37 to Sep W38
1.9.4 | Documentation and Final Submission
2.1 | System Operations & Configuration
2.1.1 | Offline Mode
2.1.2 | Turnkey Onboarding & Workspace Setup | bar: Sep W38 to Sep W39
2.1.3 | Dynamic White-Label Branding
2.1.4 | Audit Logging | bar: Sep W39
2.2 | Testing & Revisions
2.2.1 | IT Expert Testing | bar: Sep W39
2.2.2 | User Acceptance Testing (UAT)
2.2.3 | System Refinement | bar: Oct W40